## Gantt Timeline
[6 empty] | May 2026 | [19 empty] | June 2026
Workstream | Task Name | Assignees | Start Date | End Date | Duration | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10
Documentation | Create Gantt Chart document | Project Manager | 2026-05-19 | 2026-05-19 | 1
Planning | Define contact manager database schema | Database | 2026-05-19 | 2026-05-20 | 2
Planning | Design user authentication flow | API | 2026-05-19 | 2026-05-20 | 2
Planning | Create Use Case diagram | Project Manager | 2026-05-19 | 2026-05-19 | 1
Planning | Create frontend wireframes and mockups | Frontend | 2026-05-19 | 2026-05-20 | 2
Documentation | Create Presentation slides | Project Manager | 2026-05-20 | 2026-05-21 | 2
Frontend Design | Design login and signup pages | Frontend | 2026-05-21 | 2026-05-21 | 1
Frontend Development | Create contact list view component | Frontend | 2026-05-21 | 2026-05-22 | 2
Frontend Development | Create contact detail view component | Frontend | 2026-05-21 | 2026-05-21 | 1
Frontend Development | Create contact form component | Frontend | 2026-05-21 | 2026-05-22 | 2
Planning | Create ERD diagram | Database | 2026-05-21 | 2026-05-21 | 1
Planning | Plan API endpoint specifications | API | 2026-05-21 | 2026-05-22 | 2
Deployment | Deploy database to production | Database | 2026-05-22 | 2026-05-22 | 1
Documentation | Mock Presentation with group | Project Manager | 2026-05-22 | 2026-05-22 | 1
Frontend Development | Create login page UI component | Frontend | 2026-05-22 | 2026-05-25 | 4
Frontend Development | Create signup page UI component | Frontend | 2026-05-22 | 2026-05-25 | 4
Backend Development | Implement user registration endpoint | API | 2026-05-25 | 2026-05-26 | 2
Backend Development | Implement user login endpoint | API | 2026-05-25 | 2026-05-26 | 2
Backend Development | Build contact creation API endpoint | API | 2026-05-25 | 2026-05-25 | 1
Backend Development | Build contact retrieval API endpoint | API | 2026-05-25 | 2026-05-25 | 1
Backend Development | Build contact update API endpoint | API | 2026-05-25 | 2026-05-25 | 1
Backend Development | Build contact deletion API endpoint | API | 2026-05-25 | 2026-05-25 | 1
Backend Development | Develop contact search functionality | API | 2026-05-26 | 2026-05-27 | 2
Integration | Integrate frontend with contact CRUD API | Frontend | 2026-05-26 | 2026-05-28 | 3
Integration | Integrate frontend with authentication API | Frontend | 2026-05-27 | 2026-05-28 | 2
Testing | Conduct end-to-end testing workflow | Project Manager | 2026-05-29 | 2026-06-01 | 4
Testing | Perform security testing on authentication | API | 2026-05-29 | 2026-05-29 | 1
Testing | Execute contact search functionality testing | Frontend | 2026-05-29 | 2026-05-29 | 1
Deployment | Deploy API to production server | API | 2026-06-02 | 2026-06-02 | 1
Deployment | Deploy frontend to production hosting | Frontend | 2026-06-02 | 2026-06-02 | 1
Documentation | Live Presentation in class | Project Manager | 2026-06-03 | 2026-06-03 | 1